## Sheet1
Estimation
NO | Task | Time(h) | Note
1 | Setup enviroment (Android + IOS) | 4
2 | Setup Application | 2
3 | Show Camera for capture Image (Oval shape on camera) | 3.5
4 | Show captured Image on editor | 3
5 | Enable moving image + zoom image | 3.5
6 | Draw Path line + enable moving Path line | 4
7 | Save Image | 3
8 | Test + Fix bug (If have) | 5
9 | Update code + config to adapt with both Android & IOS Enviroments | 4
10 | Build to Android App + IOS App | 5
11 | Release to CHPlay and AppStore | 5
Total(Hours) |  | 42
Note : - Fee for upload Android application to CHPlay : 25$ - Fee for store IOS application to APPStore : 99$/year